## Slide 1
Seattle University eServe System
Sponsor: Elizabeth O’Brien
Advising Professor: Gilles Jeffrey
Team (MSE01): Jyoti Thakur, Dawn Wang & Tsun Tsai
Notes: jyoti

## Slide 2: Agenda
Overview of e-Serve System
Business value for new e-Serve
Our Solutions
  Architecture Design
  Database Model
  Test Plan
Project Management
Demo
Lessons Learned
Q&A
Notes: jyoti

## Slide 3: Overview
Center for Service and Community Engagement (CSCE) founded in 2004
eServe is a web application to manage the volunteer opportunities and process for Seattle University.
As per Seattle University requirement – using Microsoft technologies and Cloud for eServe development.
Notes: tsun

## Slide 4: Business Value
50 local community partners
To 25 college/university by U.S. News & World Report for service-learning
70+ hours manually to manage
78% students take a service-learning course
1,500 students
75 courses
30 faculty members
Notes: tsun

## Slide 5: eServe End-to-End Workflow
Community Partner
Creates opportunity
Admin
Approves & Assign to Course
Student
Sign up for Opportunity
Community Partner
Review Evaluation
Faculty

## Slide 6
Notes: dawn

## Slide 7: Goals To Achieve
Security
Performance / Scalability
Usability
Maintainability / Extensibility
Notes: jyoti

## Slide 8: Architecture Design
Core Technology
  Visual Studio 2013 ASP.NET for SDK
  SQL Azure for data storage.
3-tiers structure
  UI - HTML, Javascript and CSS.
  Business and Data Access layer: ASP.NET C#
  Data Storage layer: SQL
  Responsive web design (RWD)
Notes: dawn

## Slide 9: Architecture Design – 3-tiers design
Notes: dawn

## Slide 10
Notes: dawn

## Slide 11
Notes: jyoti

## Slide 12: Database
Stored procedures
Triggers
Views

## Slide 13: Test Plan
Each user story will have test case(s)
Create end-to-end test script for acceptance testing
Continuous delivery to Azure
  User acceptance test
No automation

## Slide 14
Chart: Burn down chart (2 week sprint)
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Sprint 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint 2 | 30 | 30 | 30 | 30 | 30 | 30 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0
Sprint 3 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 5
Sprint 4 | 60 | 60 | 60 | 60 | 60 | 60 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 10
Sprint 5 | 60 | 60 | 60 | 60 | 60 | 60 | 70 | 70 | 75 | 65 | 65 | 65 | 65 | 5
Ideal | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 30 | 25 | 20 | 15 | 10 | 5 | 0
Notes: 2 Weeks
Sprint 1 – Nothing added
Sprint 2 – Added tasks / flushing out requirements / VSO creation / source control
Sprint 3 – Added tasks, experimenting, mostly waiting for backend stuff
Sprint 4 – Added tasks for development work
Sprint 5 – Added tasks for development and presentation (spike at end as we realize more stuff are required)

## Slide 15: Team Stats
Velocity = 2 large + 1 medium user stories (28 hours per sprint per person average | should increase next quarter)
(Small = 4 hours, Medium = 8 hours, Large = 12 hours)
Business Value = 17/117 (first quarter)
(MVP is subset of 117)
Notes: Tsun
Velocity can increase

## Slide 16
Demo
Notes: Dawn/Jyoti/tsun
Opportunity List page
Opportunity Edit page
Student
Profile/Current/History

## Slide 17: Lessons Learned
Commit to only working on user stories assigned to each sprint
Assigning tasks to User stories
More consistency in team communication & schedule

## Slide 18
Q & A

## Slide 19: Resources
VSO site - https://eservesu.visualstudio.com
Notes: Scope, goals and requiremetns
Horizontal or vertical stack
Team picture